## Dashboard
Smart Project Risk Monitor — PM Dashboard
Metric | Value | Risk Level | Count | Project | Overall Risk Level
Total Projects | 5 | Critical | 3 | MFA Rollout | Critical
Open / Monitoring Risks | 10 | High | 4 | Vulnerability Remediation | Critical
Critical Risks | 3 | Medium | 3 | Audit Evidence Collection | Critical
High Risks | 4 | Low | 0 | Access Control Cleanup | High
Medium Risks | 3 |  |  | Vendor Security Review | High
Overdue Risks | 0
Escalations Needed | 3
Blocked Tasks | 3
Stale Task Updates | 5
Risk Category | Count | Project | Open Risks
Delivery | 2 | MFA Rollout | 2
Security | 2 | Vulnerability Remediation | 2
Compliance | 2 | Audit Evidence Collection | 2
Dependency | 1 | Access Control Cleanup | 2
Resource | 1 | Vendor Security Review | 2
Ownership | 1
Communication | 1
AI Prompt Starter
You are a Product Manager reviewing a cybersecurity project risk register. Analyze the open risks and tasks. Identify the top risks, explain why they matter, assign an overall risk level, recommend PM next actions, and write a concise stakeholder update. Focus on delivery, compliance, ownership gaps, dependencies, and escalation needs.

## Projects
Project ID | Project Name | Project Owner | Business Goal | Start Date | Target Date | Status | Completion % | Overall Risk Level | Open Risks | Critical Risks | Last Updated | Notes
P-001 | MFA Rollout | Srija Dasgupta | Improve account security before audit deadline | 2026-07-01 | 2026-08-15 | In Progress | 45% | Critical | 2 | 1 | 2026-07-03 | Focus: adoption, support readiness, stakeholder communication
P-002 | Vulnerability Remediation | Security PM | Close critical/high vulnerabilities before audit | 2026-06-20 | 2026-08-01 | Blocked | 35% | Critical | 2 | 1 | 2026-07-03 | Focus: ownership, remediation deadline, exception approvals
P-003 | Audit Evidence Collection | Compliance Lead | Prepare evidence package for cybersecurity audit | 2026-06-25 | 2026-07-28 | In Progress | 55% | Critical | 2 | 1 | 2026-07-03 | Focus: evidence readiness, missing documentation, review signoff
P-004 | Access Control Cleanup | IAM Lead | Remove stale access and validate least privilege controls | 2026-07-02 | 2026-08-10 | Not Started | 10% | High | 2 | 0 | 2026-07-03 | Focus: missing owners, access review completion
P-005 | Vendor Security Review | Procurement PM | Complete vendor questionnaire and security review | 2026-07-01 | 2026-07-25 | In Progress | 50% | High | 2 | 0 | 2026-07-03 | Focus: vendor dependency, questionnaire completion, legal review

## Risk Register
Risk ID | Project Name | Risk Category | Risk Description | Impact | Probability | Risk Score | Risk Level | Risk Owner | Due Date | Days Until Due | Mitigation Plan | Escalation Needed? | Status | Last Updated | PM Notes
R-001 | MFA Rollout | Compliance | MFA adoption is below target before audit deadline | 5 | 4 | 20 | Critical | Srija Dasgupta | 2026-07-20 | 15 | Create adoption tracker, schedule manager reminders, prepare exception process | Yes | Open | 2026-07-03 | PM focus: adoption trend and leadership visibility
R-002 | Vulnerability Remediation | Security | Critical vulnerabilities remain unresolved close to remediation deadline | 5 | 5 | 25 | Critical | Security Lead | 2026-07-18 | 13 | Prioritize critical findings, assign owners, escalate exceptions | Yes | Open | 2026-07-03 | PM focus: ownership and time-to-remediate
R-003 | Audit Evidence Collection | Delivery | Audit evidence is spread across multiple teams and not centrally validated | 4 | 4 | 16 | Critical | Compliance Lead | 2026-07-17 | 12 | Create evidence checklist and central folder; confirm evidence owners | Yes | Monitoring | 2026-07-03 | PM focus: readiness and documentation quality
R-004 | Access Control Cleanup | Ownership | Access review has missing business owners for several applications | 4 | 3 | 12 | High | IAM Lead | 2026-07-24 | 19 | Map application owners and escalate owner gaps to leadership | No | Open | 2026-07-03 | PM focus: accountability gaps
R-005 | Vendor Security Review | Dependency | Vendor security questionnaire is incomplete and may delay approval | 3 | 4 | 12 | High | Procurement PM | 2026-07-15 | 10 | Send follow-up to vendor; define internal deadline and backup approval path | No | Monitoring | 2026-07-03 | PM focus: external dependency
R-006 | MFA Rollout | Communication | End-user training materials are not finalized | 3 | 3 | 9 | Medium | Training Lead | 2026-07-22 | 17 | Finalize FAQ and support scripts; publish launch communication | No | Open | 2026-07-03 | PM focus: rollout readiness
R-007 | Vulnerability Remediation | Resource | Security engineers are overloaded with remediation and audit support | 4 | 3 | 12 | High | Security PM | 2026-07-21 | 16 | Rebalance workload; defer low-risk items; request temporary support | No | Open | 2026-07-03 | PM focus: capacity planning
R-008 | Audit Evidence Collection | Compliance | Policy review signoff is pending from legal/compliance stakeholders | 4 | 2 | 8 | Medium | Compliance Lead | 2026-07-19 | 14 | Schedule signoff review; document open questions and due dates | No | Monitoring | 2026-07-03 | PM focus: signoff dependency
R-009 | Access Control Cleanup | Security | Stale privileged accounts may remain active after cleanup deadline | 5 | 3 | 15 | High | IAM Lead | 2026-07-30 | 25 | Generate privileged account list; review exceptions weekly | No | Open | 2026-07-03 | PM focus: control effectiveness
R-010 | Vendor Security Review | Delivery | Legal review may not complete before vendor onboarding decision | 3 | 3 | 9 | Medium | Legal Partner | 2026-07-23 | 18 | Confirm legal SLA; prepare decision-ready summary for approvers | No | Open | 2026-07-03 | PM focus: timeline risk
Formulas:
Days Until Due = [Due Date]-TODAY()

## Tasks
Task ID | Project Name | Task Name | Task Owner | Priority | Status | Due Date | Days Until Due | Blocked? | Blocker Reason | Last Update | Stale Update? | PM Notes
T-001 | MFA Rollout | Confirm user groups for phased rollout | IAM Lead | High | In Progress | 2026-07-10 | 5 | No |  | 2026-07-02 | No | Needed before comms plan
T-002 | MFA Rollout | Finalize training FAQ | Training Lead | Medium | Blocked | 2026-07-12 | 7 | Yes | Waiting for help desk support script | 2026-06-27 | Yes | Escalate in weekly status
T-003 | Vulnerability Remediation | Assign critical vulnerability owners | Security Lead | Critical | Blocked | 2026-07-09 | 4 | Yes | Application owner list incomplete | 2026-06-28 | Yes | PM to push ownership mapping
T-004 | Vulnerability Remediation | Validate remediation evidence | Security Analyst | High | Not Started | 2026-07-18 | 13 | No |  | 2026-07-01 | No | Start after fixes complete
T-005 | Audit Evidence Collection | Create audit evidence checklist | Compliance Lead | High | Done | 2026-07-05 | 0 | No |  | 2026-07-03 | No | Template created
T-006 | Audit Evidence Collection | Collect policy review signoffs | Compliance Lead | High | In Progress | 2026-07-16 | 11 | No |  | 2026-06-29 | Yes | Needs legal/compliance signoff
T-007 | Access Control Cleanup | Map app owners for access reviews | IAM Lead | High | Blocked | 2026-07-14 | 9 | Yes | Missing owner data for legacy apps | 2026-06-26 | Yes | Potential escalation
T-008 | Access Control Cleanup | Review privileged accounts | IAM Analyst | Critical | Not Started | 2026-07-22 | 17 | No |  | 2026-07-02 | No | High audit impact
T-009 | Vendor Security Review | Send vendor questionnaire follow-up | Procurement PM | Medium | In Progress | 2026-07-08 | 3 | No |  | 2026-07-03 | No | Vendor dependency
T-010 | Vendor Security Review | Prepare vendor risk decision memo | Procurement PM | Medium | Not Started | 2026-07-20 | 15 | No |  | 2026-06-25 | Yes | Use if questionnaire is late
Formulas:
Days Until Due = [Due Date]-TODAY()
Stale Update? = IF(AND([Status]<>"Done",[Status]<>"Complete",TODAY()-[Last Update]>5),"Yes","No")

## Stakeholder Updates
Update ID | Date | Project Name | Audience | Update Type | Summary | Key Risks | Decisions Needed | Action Items | Owner | Due Date | Status
U-001 | 2026-07-03 | MFA Rollout | Leadership | Weekly Status | Rollout is progressing but adoption is below the audit readiness target. | Adoption below target; training not finalized | Confirm whether exceptions need leadership approval | Finalize FAQ and publish manager reminder | Srija Dasgupta | 2026-07-10 | Open
U-002 | 2026-07-03 | Vulnerability Remediation | Security Team | Risk Escalation | Critical remediation items are at risk due to owner gaps and capacity issues. | Critical findings unresolved; overloaded engineers | Decide if low-risk work can be deferred | Assign owners and confirm remediation timeline | Security PM | 2026-07-08 | Open
U-003 | 2026-07-03 | Audit Evidence Collection | Compliance Team | Audit Update | Evidence checklist is created; signoff and centralized validation remain pending. | Evidence scattered; signoff dependency | Confirm signoff owners | Collect missing evidence and schedule signoff review | Compliance Lead | 2026-07-12 | Monitoring

## AI Risk Summary
Summary ID | Date Generated | Project Name | Overall Project Health | Top Risks | Risk Level | Why It Matters | Recommended PM Actions | Escalation Recommendation | Stakeholder Summary | Generated By | Notes
AI-001 | 2026-07-03 | Vulnerability Remediation | At Risk | Critical vulnerabilities remain unresolved; owner mapping is incomplete; security team capacity is constrained. | Critical | Audit readiness and remediation deadlines may be missed if ownership is not resolved quickly. | Escalate owner gaps, prioritize critical findings, document exceptions, and confirm revised remediation dates. | Escalate to Security Leadership this week. | Vulnerability remediation is currently Critical due to unresolved findings and ownership gaps. PM action is needed to confirm owners and remediation dates. | Manual ChatGPT | Sample PM-style AI summary
AI-002 | 2026-07-03 | MFA Rollout | Watch Closely | Adoption is below target and training materials are not finalized. | High | Low adoption could create audit exceptions and support burden during rollout. | Publish FAQ, send manager reminders, track adoption by group, and define exception process. | Escalate if adoption does not improve by next checkpoint. | MFA rollout is High risk due to adoption and communication readiness gaps. | Manual ChatGPT | Sample PM-style AI summary

## Lists
Status | Priority | Risk Level | Risk Category | Audience | Update Type | Generated By | Yes/No
Not Started | Low | Low | Delivery | Leadership | Weekly Status | Manual ChatGPT | Yes
In Progress | Medium | Medium | Security | Engineering | Risk Escalation | OpenAI API | No
Blocked | High | High | Compliance | Security Team | Decision Request | Google Apps Script
Complete | Critical | Critical | Dependency | Compliance Team | Executive Summary | Make.com
Done |  |  | Resource | Vendor | Audit Update
Open |  |  | Ownership | Cross-functional Team
Monitoring |  |  | Communication
Mitigated
Closed